## IOS V1(11-10-23)
Module | Issues / Suggestions | Status | Resolved by
SignUp | Select your home country only have 3 options. | done
Enter your mobile number countries library is locally uploaded library.
| While selecting your country, country code should be automatically adjusted. | done
| When i entered the mobile number for first time, it did not went to verification page. | backend issue api response Device update
| Did not send email verification code. | otp service is not working
| Verify now button doesnt work while verifying email. | otp service is not working
When i clicked verify now button (by getting code from kafka) it didnt work but then i closed the app and opened it again it logged me in automatically.
Home | Profile picture icon at home page does not show profile picture. But if i close the app and open again it shows the profile picture at home page profile icon. | done
| If i clicked multiple times on profile icon, it opened the profile multiple times. | done
| By clicking on any industry-> App crashed | done
| No description added. | done
| No price added. | done
| Data is static. | done
Profile | Cannot verify primary email. | backend issue
| Secondary email field is duplicated. | done
Secondary email was not synced with other device.
Adding secondary mobile number was failed everytime.
| While selecting gender for first time, it should not select Other by default. | done
Business profile | If I create business profile, it asks for select address but if i try to add address--> it says Empty Field
| If i go back to profile without entering addresses, my business profile was already created. | backend issue
| Cannot switch to business profile -> Alert says request timed out | backend issue
I closed the app and opened it again and my business account was selected and my personal account name was shown as Farukh chishti, but i could not switch to my account and i had to close the app.